## Sheet1
Project: Employee Onboarding Improvement
Stakeholder | Role | Power | Interest | Key concerns | Engagement Strategy | Communication Method | Frequency | Status
Sponsor | Project Sponsor | High | High | Funding, Strategic direction | Manage closely |  |  | Contacted
Priya Sharma | HR | High | High | Quality, Compliance, realistic target, cross-functional dependencies | Manage closely |  |  | Contacted
Rahul Mehta | IT Manager | Medium | High | Security, Compliance, Dependencies | Keep Informed |  |  | Contacted
Anita Nair | Facilities Manager | Medium | High | External Dependencies | Keep Informed |  |  | Contacted
Vivek Rao | Payroll Lead | Medium | High | Compliance, External Dependencies | Keep Informed |  |  | Contacted
Neha Kapoor | Compliance Manager | Medium | High | External Dependencies | Keep Informed |  |  | Contacted
Arjun Desai | Procurement Manager | Medium | High | cross-functional planning and monthly hiring forecasts | Keep Informed |  |  | Contacted
Sanjay Verma | Hiring Manager, Operations | High | High | Reliable live source of onboarding information, Employee contribution as quickly as possible | Manage closely |  |  | Contacted
Aisha Khan | Business Analyst (New Hire) | Low | High | Lack of onboarding status tracker and transparent onboarding process information | Monitor/Consult |  |  | Contacted

## Stakeholder Register
Project: Employee Onboarding Improvement
Stakeholder | Role | Power | Interest | Key Concerns | Engagement Strategy | Communication Method | Frequency | Current Engagement Status
Project Sponsor | Director – Human Resources | High | High | Business outcomes, budget approval, project success | Manage Closely | Steering Committee Meeting | Weekly | Engaged
HR Lead | Human Resources | High | High | Hiring experience, process efficiency, policy compliance | Manage Closely | Workshop / Weekly Meeting | Weekly | Engaged
IT Lead | Information Technology | Medium | High | Account provisioning, system access, hardware readiness | Keep Informed | Team Meeting | Weekly | Engaged
Facilities Lead | Facilities Management | Medium | High | Workspace allocation, ID cards, seating | Keep Informed | Email / Meeting | Weekly | Engaged
Payroll Lead | Payroll | Medium | High | Payroll setup, statutory compliance | Keep Informed | Weekly Meeting | Weekly | Engaged
Compliance Lead | Legal & Compliance | Medium | High | Regulatory compliance, documentation | Keep Informed | Review Meeting | Weekly | Engaged
Procurement Lead | Procurement | Medium | High | Laptop and equipment procurement | Keep Informed | Email | Weekly | Engaged
Hiring Managers | Business Functions | High | High | Candidate readiness, joining timelines | Manage Closely | Workshops / Review Meetings | Bi-weekly | Engaged
New Hire Representatives | Employee Representatives | Low | High | Smooth onboarding experience, communication, visibility | Consult | Survey / Feedback Session | At Key Milestones | Engaged