## Gantt Chart
Activity ID | Activity | Duration | Start (ES) | Finish (EF) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44
A01 | Project Charter Approval | 2 | 0 | 2 | bar: D1 to D2
A02 | Project Kick-off Meeting | 1 | 2 | 3 | bar: D3
A03 | HR Discovery | 3 | 3 | 6 | bar: D4 to D6
A04 | IT Discovery | 2 | 3 | 5 | bar: D4 to D5
A05 | Facilities Discovery | 2 | 3 | 5 | bar: D4 to D5
A06 | Payroll & Compliance Discovery | 2 | 3 | 5 | bar: D4 to D5
A07 | Procurement Discovery | 2 | 3 | 5 | bar: D4 to D5
A08 | Hiring Manager Interviews | 3 | 3 | 6 | bar: D4 to D6
A09 | New Hire Interviews | 2 | 3 | 5 | bar: D4 to D5
A10 | Current State Analysis | 3 | 6 | 9 | bar: D7 to D9
A11 | Root Cause Analysis | 2 | 9 | 11 | bar: D10 to D11
A12 | Gap Analysis | 2 | 11 | 13 | bar: D12 to D13
A13 | Design Future-State Process | 4 | 13 | 17 | bar: D14 to D17
A14 | Validate Future-State Process | 3 | 17 | 20 | bar: D18 to D20
A15 | Develop Implementation Plan | 4 | 20 | 24 | bar: D21 to D24
A16 | Estimate Budget & Resources | 3 | 24 | 27 | bar: D25 to D27
A17 | Pilot Implementation | 5 | 27 | 32 | bar: D28 to D32
A18 | User Training | 3 | 32 | 35 | bar: D33 to D35
A19 | Full Rollout | 5 | 35 | 40 | bar: D36 to D40
A20 | Project Monitoring & Control | 10 | 32 | 42 | bar: D33 to D42
A21 | Project Closure & Lessons Learned | 2 | 42 | 44 | bar: D43 to D44
LEGEND
Critical path
Non-critical