## RAID Log
Project: Employee Onboarding Improvement
ID | Type | Description | Impact | Probability | Owner | Response/Mitigation | Status
R1 | Risk | Delays in procurement of laptops and accessories | High | Medium | Procurement | Order equipment early and track weekly | Open
R2 | Risk | Background verification takes longer than expected | High | Medium | Compliance | Start verification immediately after acceptence | Open
R3 | Risk | Hiring Manager approval delays | High | High | Hiring Manager | Set approval SLA andautomated reminders | Open
R4 | Risk | Inconsistent onboarding processes across locations | Medium | High | HR | Standardize onboarding checklist and SOP | Open
A1 | Assumption | Departments will provide historical onboarding data on time | Medium | Medium | All Stakeholders | Confirm availability during discovery | Open
I1 | Issue | Different departments define "onboarding completion" differently | High | High | Sponsor | Agree on one standard project definitiin | Open
D1 | Dependency | Employee submits required documents before joining | High | Medium | Employee | Send reminders and checklists before joining | Open
D2 | Dependency | External background verification vendor completes checks on time | High | Medium | Compliance | Monitor vendor SLA | Open
D3 | Dependency | Hiring Manager approves hardware and software requirements | High | Medium | Hiring Manager | Approval required before procurement begins | Open
RAID Review Frequency: Weekly Project Status Meeting