## Risk Register
Project: Employee Onboarding Improvement – Risk Register
Risk ID | Category | Risk Description | Probability | Impact | Risk Score | Risk Owner | Response Strategy | Mitigation / Contingency | Status | Trigger
RR-001 | Schedule | Background verification delays | Medium | High | 6 | Compliance Lead | Mitigate | Initiate checks immediately after offer acceptance | Open | Vendor turnaround exceeds SLA
RR-002 | Resource | Hiring Manager approval delays | High | High | 9 | HR Manager | Mitigate | Approval SLA and automated reminders | Open | Approvals exceed 2 working days
RR-003 | Procurement | Laptop delivery delays | Medium | High | 6 | IT Manager | Mitigate | Order equipment in advance; maintain buffer stock | Open | Supplier misses committed date
RR-004 | Scope | Unplanned onboarding requirements | Medium | Medium | 4 | Project Manager | Avoid | Route requests through Change Control process | Monitoring | Stakeholder requests outside baseline scope
RR-005 | Compliance | Mandatory policy changes during project | Low | High | 3 | Compliance Lead | Accept | Assess impact and raise change request if needed | Monitoring | New regulatory guidance issued
RR-006 | Adoption | Low user adoption of new process | Medium | Medium | 4 | HR Lead | Mitigate | Training sessions and user guides | Open | Negative pilot feedback