## Change Request Log
Project: Employee Onboarding Improvement
Change ID | Date | Requested By | Change Description | Reason | Impact | Decision | Approved By | Status
CR-001 | 10-Aug-2026 | HR Director | Add remote onboarding workflow | Increase in hybrid employees | Scope | Approved | Project Sponsor | Closed
CR-002 | 12-Aug-2026 | IT Manager | Include laptop asset tracking | Reduce missing assets | Scope, Cost | Approved | Project Sponsor | Closed
CR-003 | 14-Aug-2026 | Compliance Lead | Add document retention step | New compliance requirement | Scope, Time | Approved | Project Sponsor | Closed
CR-004 | 18-Aug-2026 | HR Manager | Add onboarding satisfaction survey | Measure onboarding effectiveness | Scope | Pending | Steering Committee | Open