## Lessons Learned
Project: Employee Onboarding Improvement – Lessons Learned Register
Lesson ID | Category | Lesson Learned | Recommendation | Owner | Project Phase | Date | Status
LL-001 | Planning | Early stakeholder engagement reduced rework. | Conduct stakeholder workshops before planning. | PM | Planning | 20-Aug-2026 | Closed
LL-002 | Schedule | Parallel discovery shortened timelines. | Identify parallel activities early. | PM | Planning | 22-Aug-2026 | Closed
LL-003 | Risk | Weekly RAID reviews improved visibility. | Review RAID weekly. | PM | Monitoring | 25-Aug-2026 | Closed
LL-004 | Change | Formal change control prevented scope creep. | Use Change Request process consistently. | Sponsor | Execution | 28-Aug-2026 | Closed
LL-005 | Training | Pilot feedback improved rollout quality. | Pilot before enterprise rollout. | HR Lead | Execution | 30-Aug-2026 | Closed